## Settings
Project Materials Requirements and Change Control WorkBook
This workbook maintains an accurate, up-to-date record of project material requirements and change orders. It preserves the original project takeoff, logs approved additions, deductions, and substitutions, and generates the current material requirements list. Compare requirements against actual quantities ordered, received, and used — potential discrepancies are flagged for quick investigation and correction.
More information and instructions
Connect To QR Inventory
With QR Inventory, field and warehouse teams can quickly record material receiving, transfers, and usage by project through the mobile app, using fast bulk scanning and voice control. When the workbook is connected to QR Inventory, inventory activity can be imported automatically and compared to current project material requirements. This helps you see at a glance what has been ordered, received, and used, and what remains available; identify shortages, over-ordering, excess usage, and other discrepancies; and reduce manual data entry between the field and the office.
More Info On QR Inventory
Project Summary
Metric | Value | Meaning | Workbook Spreadsheets Descrption
Project ID | PRJ-2026-014 | Project ID for this workbook | Settings
Project Name | Riverside Office | Descriptive project name | Contains project summary to show you the big picture – what did you spend on the materials fr his project up to date, projected remaining cost, and how it compares to the original takeoff. Automatically updates with entered changes.
Takeoff line items | 5 | Number of line items in takeoff list
Takeoff total cost | 7137.5 | Total originally estimated materials cost | A_Takeoff
Current active line items | 5 | Current number of active line items (original takeoff items plus new added items minus deleted items) | Original takeoff list – should be entered or imported at the start of the project and frozen, becoming a project budget baseline.
Cost Of Received Materials Up To Date | 6713.5 | Actual cost of materials received so far (if actual inventory data is available) | B_Changes
Estimated Remaining Cost | 1323 | Estimated Remaining cost of outstanding materials based on last known price | Changes log – enter all changes here. Only changes with status=Approved affect C_Current_Materials_List
Projected Final Cost | 8036.5 | Projected final materials cost based on cost of materials received up to date and estimated cost of outstanding materials | C_Current_Materials_List
Projected Deviation From Budget | 899 | Projected deviation from original budget | It is the live current materials list. You do not enter anything there - it is automatically composed from data in other lists (A,B and D)
Projected % Deviation From Budget | 12.6% | Projected percent deviation from original budget | D_Actual_Inventory_Data
These are actual inventory purchases, receiving and usage data, that can be automatically imported from QR Inventory software, or entered manually. This data automatically flows into the current materials list (C), allowing you to compare project requirements with actual materials receiving and usage, review costs, and quickly identify shortages, overages, and potential usage discrepancies.
More instructions for this template

## A_Takeoff
Item ID | Description | Category | Cost Code | Notes | UOM | Qty | Unit Price | Extended Cost
MAT-LUM-001 | SPF Stud, 2 × 4 × 8 ft | Framing Lumber | 06-100 | Interior partition framing | EA | 240 | 4.85 | 1164
MAT-DW-001 | Drywall Panel, 1/2 in × 4 × 8 ft | Drywall | 09-290 | Interior walls and ceilings | SHEET | 180 | 13.75 | 2475
MAT-PLB-001 | Copper Pipe, Type L, 3/4 in × 10 ft | Plumbing | 22-100 | Domestic water supply lines | EA | 32 | 39.5 | 1264
MAT-ELE-001 | LED Troffer Light, 2 × 4 ft, 40 W | Electrical | 26-510 | Office suspended-ceiling lighting | EA | 24 | 78 | 1872
MAT-CON-001 | Concrete Mix, 80 lb Bag | Concrete | 03-300 | Equipment pads and minor repairs | BAG | 50 | 7.25 | 362.5

## B_Changes
Item ID | Description | Category | Cost Code | UOM | Action | Qty Change | Current Unit Price | Extended Cost Change | Reason For The Change | Status | Requested By | Request Date | Decision By | Decision Date
MAT-INS-001 | Fiberglass Batt Insulation | Insulation | 07-210 | BAG | New Item | 36 | 10 | 360 |  | Approved
MAT-LUM-001 | SPF Stud, 2 × 4 × 8 ft | Framing Lumber | 06-100 | EA | Qty Change (+/-) | 40 | 4.85 | 194 |  | Approved
MAT-ELE-001 | LED Troffer Light, 2 × 4 ft, 40 W | Electrical | 26-510 | EA | Qty Change (+/-) | -24 | 78 | -1872 |  | Approved
MAT-CON-001 | Concrete Mix, 80 lb Bag | Concrete | 03-300 | BAG | Qty Change (+/-) | -40 | 7.25 | -290 |  | Pending
MAT-INS-001 |  |  |  |  | Qty Change (+/-) | -6 | 11 | -66 |  | Approved

## C_Current_Materials_List
Item ID | Description | Category | Cost Code | Notes | UOM | Qty | Last Known Unit Price | Budgeted Unit Price | Qty Ordered Up To Date | Total PO Cost Up To Date | Qty Received Up To Date | Qty On Order | Cost Of Items Received Up To Date | Qty Used Up To Date | Available On-Hand | Scrap/Waste | Cost Of Scrap / Waste | Outstanding Qty | Estimated Remaining Cost | Estimated Total Cost | Original Budgeted Cost | Deviation From Original Budget | % Deviation From Original Budget | Attention / Validation
MAT-LUM-001 | SPF Stud, 2 × 4 × 8 ft | Framing Lumber | 06-100 | Interior partition framing | EA | 280 | 4.85 | 4.85 | 250 | 1212.5 | 200 | 50 | 970 | 150 | 40 | 10 | 48.5 | 90 | 436.5 | 1406.5 | 1164 | 242.5 | 20.83%
MAT-DW-001 | Drywall Panel, 1/2 in × 4 × 8 ft | Drywall | 09-290 | Interior walls and ceilings | SHEET | 180 | 13.75 | 13.75 | 180 | 2475 | 150 | 30 | 2062.5 | 120 | 30 | 0 | 0 | 30 | 412.5 | 2475 | 2475 | 0 | 0%
MAT-PLB-001 | Copper Pipe, Type L, 3/4 in × 10 ft | Plumbing | 22-100 | Domestic water supply lines | EA | 32 | 39.5 | 39.5 | 30 | 1185 | 20 | 10 | 790 | 12 | 8 | 0 | 0 | 12 | 474 | 1264 | 1264 | 0 | 0%
MAT-ELE-001 | LED Troffer Light, 2 × 4 ft, 40 W | Electrical | 26-510 | Office suspended-ceiling lighting | EA | 0 | 78 | 78 | [9 empty] | 0 | 0 | 0 | 1872 | -1872 | -100%
MAT-CON-001 | Concrete Mix, 80 lb Bag | Concrete | 03-300 | Equipment pads and minor repairs | BAG | 50 | 7.25 | 7.25 | 60 | 456 | 60 | 0 | 456 | 52 | 8 | 0 | 0 | -10 | 0 | 456 | 362.5 | 93.5 | 25.79% | Ordered is more than needed; Received is more than needed; Used is more than needed
MAT-INS-001 | Fiberglass Batt Insulation | Insulation | 07-210 |  | BAG | 30 | 11 | 0 | 40 | 2200 | 36 | 4 | 1980 | 30 | 6 | 0 | 0 | -6 | 0 | 1980 | 0 | 1980 | 100% | Ordered is more than needed; Received is more than needed

## D_Actual_Inventory_Data
Item ID | Description | Category | UOM | Unit Price | Ordered Qty | Total PO Cost | Received Qty | Actual Cost Of Received Items | Used Qty | On-Hand Qty | Scrap/Waste
MAT-LUM-001 | SPF Stud, 2 × 4 × 8 ft | Framing Lumber | EA | 4.85 | 250 | 1212.5 | 200 | 970 | 150 | 40 | 10
MAT-DW-001 | Drywall Panel, 1/2 in × 4 × 8 ft | Drywall | SHEET | 13.75 | 180 | 2475 | 150 | 2062.5 | 120 | 30 | 0
MAT-PLB-001 | Copper Pipe, Type L, 3/4 in × 10 ft | Plumbing | EA | 39.5 | 30 | 1185 | 20 | 790 | 12 | 8 | 0
MAT-CON-001 | Concrete Mix, 80 lb Bag | Concrete | BAG | 7.6 | 60 | 456 | 60 | 456 | 52 | 8 | 0
MAT-INS-001 | Fiberglass Batt Insulation, R-13, 15 in × 93 in | Insulation | BAG | 55 | 40 | 2200 | 36 | 1980 | 30 | 6 | 0
MAT-ELE-002 | EMT Conduit, 3/4 in × 10 ft | Electrical | EA | 9.1 | 80 | 728 | 50 | 455 | 35 | 15 | 0

## Lists
Qty Change (+/-)
New Item